SPRINT 1

# Sprint 1 tasks 2.0

Accessible Job Interview System

Team Savage 17
University of North Texas Capstone
Planning date: September 30, 2026

Sprint 1 planning purpose Define the Sprint 1 MVP, identify the first high-priority user stories, break those stories into assignable development tasks, and give every team member clear ownership while preserving cross-team collaboration.

# 1. What Sprint 1 Is Supposed to Accomplish

Sprint 1 should deliver a working vertical slice of the core interview experience. A user should be able to configure a technical mock interview, receive technical questions, type and submit answers, have the session and responses saved, and receive a rule-based score and feedback when the interview ends.

Sprint 1 demo target Start interview -> configure technical session -> receive one question at a time -> submit text answers -> persist session/responses -> keyword evaluation -> final score and feedback -> retry or start a new session.

## Sprint 1 scope that should be completed

Technical interviews only for the Sprint 1 interview flow.

Text-only answers; voice input is deferred to a later sprint.

A 50-question technical question library stored in PostgreSQL.

Interview setup that includes job title, supported difficulty, and a 15/30/45-minute timer.

Questions displayed one at a time with a visible progress indicator.

Rule-based keyword matching for answer evaluation.

A running correct count may be shown during the interview; full scoring is shown after the interview ends.

Final results include an overall score and feedback for individual answers.

Interview sessions and responses persist in Supabase/PostgreSQL.

The application is deployable through Render and validated through automated/manual QA.

## Confirmed Sprint 1 technology stack

| Layer | Technology | Sprint 1 use |
| --- | --- | --- |
| Front end | Next.js | Interview setup, question/answer flow, results and accessible UI |
| Back end | FastAPI (Python) | Session logic, API endpoints, question retrieval, scoring/feedback services |
| Database / data platform | Supabase + PostgreSQL | Questions, sessions, responses, feedback and user-linked data |
| Hosting | Render | Deploy the Next.js/FastAPI application and staging/demo environment |
| Testing | Pytest + FastAPI TestClient + Playwright | Unit, integration, API and end-to-end coverage |
| CI / version control | GitHub + GitHub Actions | Feature branches, pull requests and automated checks |

## Explicitly not part of the first Sprint 1 implementation

Behavioral interview track.

AI/NLP answer evaluator replacing the keyword evaluator.

Voice answer input.

Pause/resume controls.

Live, continuously updating score beyond the simple running correct count.

Lesson plans and the broader learning module.

Authentication prerequisite: The current design already shows a Log In / Create Account build. If that screen is only visual and is not yet connected to working authentication/session identity, Authentication Integration should be promoted to Priority 1 immediately because saved interview data must be associated with a user.

# 2. Why These User Stories Come First

The first five stories are intentionally ordered around one complete user journey instead of separate disconnected features. Together they validate the core architecture and produce something that can be demonstrated, tested, and improved at the end of the sprint.

They form a complete vertical slice. The sprint can demonstrate a real start-to-finish interview instead of several partial pages.

They have clear dependencies. Configuration provides context for questions; questions are needed before answers; answers must be stored before scoring and feedback are useful.

They validate every major layer. The stories exercise Next.js, FastAPI, PostgreSQL/Supabase, deployment, and testing instead of postponing integration risk.

They match the Sprint 1 design scope. Technical text interviews, the 50-question library, keyword evaluation, and post-interview results are the core Sprint 1 behaviors.

They keep advanced work from blocking the MVP. AI evaluation, voice, behavioral interviews and other enhancements can be added after the core interview loop works reliably.

## Priority 1 story order

| Order | User story | Priority | Reason for placement |
| --- | --- | --- | --- |
| 1 | US-1 Configure Technical Interview | P1 | Sets the session context used by all later interview steps. |
| 2 | US-2 Receive Interview Questions | P1 | Provides the technical content for the interview. |
| 3 | US-3 Answer Interview Questions | P1 | Creates the core interaction and user responses. |
| 4 | US-4 Save Interview Session & Responses | P1 | Proves database integration and enables stored results/history. |
| 5 | US-5 Evaluate Answers + Results/Feedback | P1 | Completes the user value with scoring and feedback. |

# 3. Sprint 1 Priority 1 User Stories

## US-1 - Configure Technical Interview

Priority: P1 - Critical  |  Story coordinator: Kobra Amiri

As a user, I want to configure a technical interview by entering my job title and selecting the interview difficulty and duration so that the practice session matches what I want to prepare for.

Why this is high priority: Every later interview action needs a session configuration. This story establishes the context for the question-selection and interview-session services.

Acceptance criteria:

The user can enter a job title.

The Sprint 1 interview type is Technical.

The user can select a supported difficulty.

The user can select a 15, 30, or 45 minute duration.

Required fields are validated and understandable error messages are shown.

Selecting Begin Interview creates or initializes the interview session and moves the user into the interview flow.

## US-2 - Receive Interview Questions

Priority: P1 - Critical  |  Story coordinator: Moshood Abisoye

As a user, I want to receive technical interview questions from the Sprint 1 question library so that I can practice answering relevant technical questions.

Why this is high priority: There is no interview without questions. This story also validates the first full data path from PostgreSQL through FastAPI to Next.js.

Acceptance criteria:

Questions are retrieved from the Sprint 1 50-question technical library.

Question selection can use the session configuration such as difficulty/category where supported.

One question is displayed at a time.

The system returns the information needed for later keyword evaluation without exposing implementation details unnecessarily to the user.

The system handles missing/failed question retrieval with a clear error state.

The first question loads when the configured interview begins.

## US-3 - Answer Interview Questions

Priority: P1 - Critical  |  Story coordinator: Jayme Nguyen

As a user, I want to type and submit answers to interview questions so that I can complete a realistic text-based mock interview.

Why this is high priority: This is the central user interaction. It converts the question library into an actual interview experience and creates the responses needed for storage and evaluation.

Acceptance criteria:

The user can type a text answer for the current question.

The user can submit the answer.

The submitted response is associated with the correct session and question.

After submission, the interview advances to the next question when appropriate.

A progress indicator shows how far the user is through the interview.

Empty or missing answers are handled consistently and can be identified later during scoring/feedback.

The interview can reach a completion state.

## US-4 - Save Interview Session & Responses

Priority: P1 - Critical  |  Story coordinator: Kieu Le

As a user, I want my interview session and responses saved so that my results can be generated and my completed interview can be retrieved later.

Why this is high priority: Persistence is required for reliable scoring, feedback, history, future progress tracking, and recovery across application sessions.

Acceptance criteria:

The session record is saved in Supabase/PostgreSQL.

Each submitted response is saved and linked to the correct session and question.

The session stores the configuration needed for the interview, including job title, interview type, difficulty and timing information as supported by the schema.

Completion state is stored when the interview ends.

Saved interview data remains available after the user leaves/logs out and returns.

Database write failures are handled safely and surfaced to the application.

## US-5 - Evaluate Answers + Results/Feedback

Priority: P1 - Critical  |  Story coordinator: Prince Nnadi

As a user, I want my completed interview responses evaluated and shown with an overall score and feedback so that I understand what I did well and what I should improve.

Why this is high priority: This completes the Sprint 1 value proposition. The user finishes the interview with an actionable result instead of only submitting answers.

Acceptance criteria:

Each submitted answer is evaluated using Sprint 1 rule-based keyword matching.

Missing/unanswered questions are recognized during scoring and feedback.

The system calculates an overall interview score.

A simple running correct count may be shown during the session; full scoring is shown after the interview ends.

The results view shows overall score and feedback for individual answers.

The user can retry/start a new session from the results flow.

The final score and feedback are persisted in PostgreSQL.

Sprint 1 does not depend on an AI/NLP evaluator to grade answers.

# 4. How Work Is Assigned

Assignment rule User stories are team-owned; tasks are individually owned. A story coordinator keeps the story moving, but no single developer should be responsible for the entire front end, back end, database, testing and integration of a large user story.

This structure lets the subteams keep their specialties while still having every group member contribute code or technical implementation. Each task should have one primary assignee, a clear deliverable, and a pull request or other verifiable output.

# 5. Sprint 1 Task Backlog and Assignments

The tasks below are the recommended first implementation backlog. Task IDs are grouped under the Priority 1 user story they support. Cross-cutting CI/deployment work is included because the stories are not complete until the integrated application can be tested and demonstrated.

## US-1 - Configure Technical Interview

| Task | Primary owner | Subteam alignment | Work to complete | Definition of task completion |
| --- | --- | --- | --- | --- |
| S1-1.1 | Kobra Amiri | PM / UX | Build the Next.js interview setup panel: job title, technical interview type, difficulty, 15/30/45 minute timer, and Begin Interview action. | Usable setup UI connected to local state/API contract. |
| S1-1.2 | Owen Erickson | Design & Architecture / AI | Create FastAPI/Pydantic request and response models plus the endpoint/service that initializes a configured interview session. | Documented endpoint that accepts valid setup data and returns a session/start response. |
| S1-1.3 | Blake Hawkins | UX / QA | Implement accessible form behavior and client-side validation for the setup flow: labels, keyboard use, focus/error states, and required-field handling. | Accessible validated form behavior merged into the setup UI. |

## US-2 - Receive Interview Questions

| Task | Primary owner | Subteam alignment | Work to complete | Definition of task completion |
| --- | --- | --- | --- | --- |
| S1-2.1 | Riket Sanketkumar Patel | AI / Tools & Infrastructure | Create and seed the Sprint 1 50-question technical library in PostgreSQL, including category/difficulty and expected keyword data needed by the evaluator. | Repeatable SQL/seed script and validated question records. |
| S1-2.2 | Moshood Abisoye | Design & Architecture / AI | Implement the FastAPI question-selection service and endpoint that retrieves the next appropriate question for the current session. | Question retrieval service/API with missing-question error handling. |
| S1-2.3 | Arvin Barghi | QA / Tools & Infrastructure | Write automated API/integration tests for question retrieval, valid selection, no-question/error conditions, and database interaction. | Pytest/FastAPI TestClient test suite for US-2. |

## US-3 - Answer Interview Questions

| Task | Primary owner | Subteam alignment | Work to complete | Definition of task completion |
| --- | --- | --- | --- | --- |
| S1-3.1 | Hongli Pan | UX / QA | Build the Next.js interview session view: current question, text-answer control, submit action, and visible progress indicator. | Responsive question-and-answer UI matching Sprint 1 flow. |
| S1-3.2 | Jayme Nguyen | PM / QA | Implement front-end to back-end answer submission and next-question flow, including session/question IDs and state transitions. | Working submit -> save/advance integration for the interview loop. |
| S1-3.3 | Hamidat Oloko | PM / QA | Write automated tests for answer submission, empty/missing answers, advancement to the next question, and relevant API errors. | Automated US-3 acceptance/integration tests and test-plan mapping. |

## US-4 - Save Interview Session & Responses

| Task | Primary owner | Subteam alignment | Work to complete | Definition of task completion |
| --- | --- | --- | --- | --- |
| S1-4.1 | Kieu Le | Design & Architecture / Tools & Infrastructure | Finalize the Supabase/PostgreSQL Sprint 1 schema and migrations for users/session linkage, sessions, questions, responses, and feedback reports needed by the first five stories. | Versioned schema/migration scripts aligned with Sprint 1 ER relationships. |
| S1-4.2 | Sublime Mpanda | QA / Tools & Infrastructure | Implement the FastAPI persistence/repository layer for creating/updating sessions and storing/retrieving responses. | Testable persistence service used by the session and answer endpoints. |
| S1-4.3 | Valeria Rodriguez Hernandez | PM / Tools & Infrastructure | Configure Supabase connection settings, Render environment variables/secrets, and a staging connection/deployment smoke test. | Working staging configuration with secrets kept out of source control. |

## US-5 - Evaluate Answers + Results/Feedback

| Task | Primary owner | Subteam alignment | Work to complete | Definition of task completion |
| --- | --- | --- | --- | --- |
| S1-5.1 | Prince Nnadi | PM / AI | Implement the rule-based KeywordEvaluator, per-answer scoring, overall score calculation, and running correct-count output needed for Sprint 1. | Deterministic evaluator with unit-testable scoring behavior. |
| S1-5.2 | Aisha Aloma | PM / AI | Implement the feedback-generation service/rules that transform scoring results into clear per-answer strengths, weaknesses, missing-answer notes, and improvement guidance. | Structured feedback payload/service consumed by the results screen. |
| S1-5.3 | Shegofa Ahmadi | UX / AI | Build the Next.js results and feedback view showing overall score, per-answer feedback, and retry/start-new-session actions. | Accessible results screen integrated with the US-5 API response. |
| S1-5.4 | Christofer Arias | QA / Tools & Infrastructure | Create Playwright end-to-end coverage for the full Sprint 1 critical path: configure -> receive question -> answer -> complete -> view saved score/feedback. | Repeatable E2E test covering the main demo workflow. |

## Cross-cutting Sprint 1 engineering

| Task | Primary owner | Subteam alignment | Work to complete | Definition of task completion |
| --- | --- | --- | --- | --- |
| S1-X.1 | Thunder Oyebi | Design & Architecture / Tools & Infrastructure | Configure GitHub Actions CI for FastAPI tests and Next.js lint/build/tests; wire in the Sprint 1 automated checks and document failure troubleshooting. | PR/push CI pipeline that blocks obvious broken builds/tests. |

# 6. Individual Ownership Summary

This table provides a quick check that every team member has a concrete Sprint 1 technical responsibility. Team leadership/PM duties continue in addition to these implementation assignments.

| Team member | Primary task | Primary Sprint 1 ownership |
| --- | --- | --- |
| Aisha Aloma | S1-5.2 | Feedback-generation service and rules |
| Hamidat Oloko | S1-3.3 | Automated answer-flow tests |
| Jayme Nguyen | S1-3.2 | Answer submission / next-question integration |
| Kobra Amiri | S1-1.1 | Interview setup UI |
| Prince Nnadi | S1-5.1 | Keyword evaluator and scoring |
| Valeria Rodriguez Hernandez | S1-4.3 | Supabase/Render staging configuration |
| Kieu Le | S1-4.1 | PostgreSQL schema and migrations |
| Moshood Abisoye | S1-2.2 | Question-selection API/service |
| Owen Erickson | S1-1.2 | Session configuration API/service |
| Thunder Oyebi | S1-X.1 | GitHub Actions CI |
| Blake Hawkins | S1-1.3 | Accessible setup validation/interaction |
| Hongli Pan | S1-3.1 | Interview question/answer UI |
| Shegofa Ahmadi | S1-5.3 | Results/feedback UI |
| Riket Sanketkumar Patel | S1-2.1 | 50-question PostgreSQL seed/library |
| Arvin Barghi | S1-2.3 | Question API/integration tests |
| Christofer Arias | S1-5.4 | Playwright E2E critical path |
| Sublime Mpanda | S1-4.2 | Session/response persistence layer |

# 7. Backlog After the First Five Stories

These stories are valuable, but they should not pull attention away from the Sprint 1 vertical slice until US-1 through US-5 are on track. Accessibility fundamentals (semantic controls, keyboard navigation, labels, focus behavior, readable errors) should still be applied while building every Priority 1 story.

| Backlog item | Recommended priority | When to pull it in | Reason |
| --- | --- | --- | --- |
| US-0 Authentication Integration / Verification | P1 if unfinished | Immediately, if login/account is not functionally connected | Persistence and history require reliable user identity. If the current build already works, only verify/integrate it. |
| US-6 Accessibility Controls (TTS, text size, theme, dyslexia-friendly font) | P2 | After core interview loop is stable, while maintaining basic accessibility throughout P1 work | Important to the product mission, but the first sprint must first prove the core interview flow. |
| US-7 Interview History / Past Results | P2 | After US-4 and US-5 | Depends on persisted completed sessions and feedback. |
| US-8 Practice Individual Questions | P2 | After question retrieval + evaluator are stable | Reuses the question/evaluator work without blocking the MVP interview flow. |
| US-9 User Statistics / Progress Tracking | P3 | Later sprint | Requires multiple saved sessions before statistics are meaningful. |
| US-10 Lesson Plans | P3 | Later sprint | Useful learning feature but separate from the Sprint 1 interview loop. |
| US-11 Behavioral Interview Track | Future | Later sprint | Updated design marks behavioral interviewing for later. |
| US-12 AI/NLP Answer Evaluator | Future | After keyword evaluator and core loop are validated | Avoids making an external AI dependency block the MVP and keeps Sprint 1 deterministic. |
| US-13 Voice Answer Input | Future | Later sprint | Sprint 1 is text-only. |
| US-14 Pause / Resume | Future | Later sprint | Sprint 1 uses fixed 15/30/45-minute timing without pause/resume. |
| US-15 Optional Live Score | Future | Later sprint | Full scoring is intentionally post-interview in Sprint 1; only a simple running correct count is needed now. |

# 8. Recommended Execution Order and Dependencies

Do not interpret the numbered stories as “finish one completely before starting the next.” The dependencies describe integration order, while developers can work in parallel on UI, APIs, database schema, evaluator logic, tests, CI, and deployment.

| Phase | Focus | Coordination note |
| --- | --- | --- |
| Step 1 | Lock API contracts + PostgreSQL schema | Owen, Kieu, Moshood, Sublime, Prince coordinate the request/response objects and IDs before parallel implementation. |
| Step 2 | Build US-1 and question seed/service in parallel | Kobra/Owen/Blake can build setup while Riket/Moshood/Arvin build and test the question path. |
| Step 3 | Build answer loop + persistence | Hongli/Jayme/Hamidat integrate with Sublime/Kieu once question/session IDs are stable. |
| Step 4 | Add scoring + feedback + results | Prince/Aisha/Shegofa connect to saved responses while the interview loop is being stabilized. |
| Step 5 | Run the complete E2E path in CI/staging | Christofer validates the user journey; Thunder/Valeria ensure CI and deployed environments are usable. |
| Step 6 | Regression and demo hardening | QA executes acceptance criteria continuously and the team fixes critical/high issues before review. |

# 9. Sprint 1 Definition of Done

A task being coded is not the same as a story being complete. A Priority 1 story should only be marked Done when the implementation, integration and verification are all complete.

Acceptance criteria for the story are implemented and demonstrable.

Code is committed on a feature branch and submitted through a pull request rather than pushed directly to main.

Relevant unit/integration/E2E tests are added and passing.

GitHub Actions checks pass.

Backend test coverage is tracked toward the QA plan target of greater than 70% where applicable.

No Critical bugs remain for the story; High-priority defects are fixed and re-tested before the Sprint Review.

The feature works against the shared Supabase/PostgreSQL environment as appropriate.

The integrated feature is usable in the Render staging/demo environment as appropriate.

Basic accessibility is verified: keyboard navigation, form labels, focus states, readable text/error messaging, and no obvious blocking accessibility issue.

Documentation/Test Case Tracker is updated so QA can reproduce what was tested.

## Working agreement for story ownership

A user story is not “assigned to one person.” The story has a coordinator, while its implementation is broken into multiple owned tasks.

Each task has one primary owner so responsibility is clear; pair programming/review is encouraged but should not make ownership ambiguous.

QA begins while development is happening, not after all coding is finished.

If a task is blocked by another task, the owner records the dependency immediately rather than waiting until the end of the sprint.

If a Priority 1 story is at risk, lower-priority backlog work should not be started simply to keep someone busy; that developer should help unblock the P1 story.

# 10. Planning Basis

This Sprint 1 task plan was prepared from the project's Sprint 0 team assignments, the updated Product Design document, the QA Sprint Test Plan, the Requirements document, and the Tools & Infrastructure documentation. The confirmed implementation stack for this plan is Next.js + FastAPI + Render + Supabase/PostgreSQL as agreed by the team.

Next planning action Copy the task IDs into Trello/GitHub, add acceptance criteria to each story card, and have each primary owner confirm that the task scope and dependencies are understood before Sprint 1 development begins.